## Summary
BillBandit iOS Ink Feature Status Tracker
Canonical workbook updated 2026-06-22. Scope is the blue/cream native iOS ink build; web interface findings are deferred.
Metric | Value | Status | Story Count | Finding Count
iOS user stories | 22 | Tested pass | 21
Stories tested pass | 21 | Needs focused test | 0
Stories pending focused tests | 0 | Needs focused UI test | 0
Fixed iOS findings | 10 | Deferred by scope | 1
Pending iOS coverage findings | 0 | Fixed |  | 10
Deferred web items | 2 | Pending |  | 0
Railway production URL | https://billbandit-api.contenthelper.in | Deferred |  | 1
Latest iOS regression status | Passed
Current iOS Test Loop
1 | Created dedicated simulator BillBandit Ink QA - Codex and used only that simulator for final iOS evidence.
2 | Fixed remote add-member email contract, profile tab/logout UX, bottom-tab hit targets, final-bill launch state, and split-row keyboard/ScrollView tap handling.
3 | Expanded Railway UI coverage for OTP/profile/logout, ledger create/add/edit/delete/finalize, add-friend-by-email, two-person split, settlement row, and record payment.
4 | Normal iOS suite passed on the dedicated simulator: 13 passed, 0 failed, 3 Railway UI tests skipped by opt-in guard.
5 | Live Railway UI suite passed 3/3 against https://billbandit-api.contenthelper.in on the dedicated simulator.
Remaining | Native tab UI is deferred because this pass is scoped to the blue/cream ink build.
Scope | Web interface testing/fixes are intentionally deferred by user request.

## iOS User Stories
ID | Surface | Area | User Story | Expected Behaviour | Code Evidence | Test Evidence | Priority | Feature Status | Test Status | Errors / Observations | Fix Status | Retest Status
IOS-INK-001 | iOS Ink | Launch and Auth Routing | As a signed-out iOS user, I land on the ink welcome/auth flow; as a signed-in complete-profile user, I land in the ink trips shell. | Root restores auth, resets/uses volatile sessions from launch args, routes signed-out users to welcome/auth, incomplete users to profile completion, and complete users to the ink app shell. | apps/ios/BillBanditApp/Sources/BillBanditApp.swift; apps/ios/BillBanditApp/Sources/AuthStore.swift | testAppLaunches; testMockAppleAuthCompletesProfileAndReachesTrips; testRailwayOTPAuthSignsIntoReceiptTrips | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-002 | iOS Ink | Welcome | As a new or returning user, I can start login from the blue/cream ink welcome screen. | Welcome exposes the login CTA; tapping it enters the configured auth destination rather than mutating local data directly when auth callbacks are supplied. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift; apps/ios/BillBanditApp/Sources/BillBanditApp.swift | testMockAppleAuthCompletesProfileAndReachesTrips; testRailwayOTPAuthSignsIntoReceiptTrips | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-003 | iOS Ink Auth | OTP Start | As an iOS user, I can enter a phone or email identifier and request an OTP from Railway. | Auth start trims the identifier, calls /api/mobile/auth/otp/start, stores the challenge, and advances to OTP verification only on success. | apps/ios/BillBanditApp/Sources/InkAuthFlowView.swift; apps/ios/BillBanditApp/Sources/AuthStore.swift | testRailwayOTPAuthSignsIntoReceiptTrips against https://billbandit-api.contenthelper.in | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-004 | iOS Ink Auth | OTP Verify | As an iOS user, I can enter a 6-digit OTP and sign in to the Railway-backed account. | OTP code input filters to six digits; submit calls /api/mobile/auth/otp/verify, applies token/user, clears the challenge, and routes by profile completion. | apps/ios/BillBanditApp/Sources/InkAuthFlowView.swift; apps/ios/BillBanditApp/Sources/AuthStore.swift | testRailwayOTPAuthSignsIntoReceiptTrips passed with API_BASE_URL=https://billbandit-api.contenthelper.in | P0 | Implemented | Tested pass | The first live assertion only accepted empty-state copy; real Railway data can land on a non-empty trips list. | Fixed | Passed
IOS-INK-005 | iOS Ink Auth | Apple Sign-In and Profile Completion | As an iOS user, I can use Apple sign-in and complete required profile fields before entering the app. | Mock/system Apple modes are supported; profile completion requires name and UPI ID, saves via AuthStore, then enters trips. | apps/ios/BillBanditApp/Sources/BillBanditApp.swift; apps/ios/BillBanditApp/Sources/InkAuthFlowView.swift | testMockAppleAuthCompletesProfileAndReachesTrips; testProfileCompletionRequiresUPI | P0 | Implemented | Tested pass | XCTest saw duplicate keyboard toolbar Done buttons; helper now taps first resolved match. | Fixed | Passed
IOS-INK-006 | iOS Ink Trips | Empty Trips | As a new ink app user, I see an empty trips state and can start a new trip ledger. | TripsEmpty shows No tabs running, mascot art, bottom tabs, top-right add, and Start a trip CTA. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testMockAppleAuthCompletesProfileAndReachesTrips; testPrototypeLedgerCanAddEditAndDeleteExpense | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-007 | iOS Ink Trips | Live Trips List | As a signed-in Railway user with existing groups, I can land on a non-empty trips list. | YourTrips renders TripCard rows for remote groups, including title, dates, member/entry counts, open/final stamp, total, and net balance. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayOTPAuthSignsIntoReceiptTrips now accepts tripCard.* rows from real data | P0 | Implemented | Tested pass | Original test assumed no real data and missed this valid state. | Fixed | Passed
IOS-INK-008 | iOS Ink Ledger | Create Railway Ledger | As a signed-in Railway-backed ink app user, I can create a new ledger from the trips shell. | NewLedger captures title/date context; in remote mode opening posts /api/mobile/groups, maps the returned group, and routes to the live ledger. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanCreateEditDeleteAndFinalizeInkLedger against https://billbandit-api.contenthelper.in | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-009 | iOS Ink Ledger | Remote Ledger Sync | As a signed-in ink user, my ledgers load from Railway mobile groups. | InkTripStore configures with APIClient/current user, reloads /api/mobile/groups, fetches detail, maps groups to trips, and shows loading/error banners. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift; apps/ios/BillBanditApp/Sources/APIClient.swift | testRailwayOTPAuthSignsIntoReceiptTrips; testRailwayCanCreateEditDeleteAndFinalizeInkLedger; BillBanditTests.testInkStoreRunsLedgerFlowThroughMobileAPIClient | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-010 | iOS Ink Members | Add Friend by Email | As a remote-backed ink ledger user, I can add a registered member by BillBandit email. | AddFriend collects email, validates /api/mobile/users/lookup?email=..., submits email to /api/mobile/groups/{id}/members, and shows found/not-found states. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift; apps/ios/BillBanditApp/Sources/MockBillBanditAPI.swift; apps/web/app/api/mobile/users/lookup/route.ts | testRailwayCanAddFriendSplitExpenseAndRecordSettlement seeds a registered friend, validates Account found, and adds the friend through iOS UI | P0 | Fixed | Tested pass | Code previously used username lookup/submission against an email-only member route. | Fixed | Passed
IOS-INK-011 | iOS Ink Ledger | Live Ledger Empty State | As a ledger user with no entries, I can see the ledger empty state and add the first entry. | LiveLedger shows ledger.empty copy when there are no expenses and exposes ledger.addEntry. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanCreateEditDeleteAndFinalizeInkLedger asserts ledger.empty after live Railway expense deletion | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-012 | iOS Ink Entries | Add Entry | As an ink ledger user, I can add an equal-split expense entry. | AddEntry requires title, amount > 0, at least one split member, selected payer, computes equal split preview, and saves into the ledger. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanCreateEditDeleteAndFinalizeInkLedger; testRailwayCanAddFriendSplitExpenseAndRecordSettlement | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-013 | iOS Ink Entries | Edit Entry | As an ink ledger user, I can edit an existing entry and return to the updated ledger row. | Opening an expense populates AddEntry in edit mode; Update ledger saves changes, clears editing state, and returns to live ledger. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanCreateEditDeleteAndFinalizeInkLedger edits a live Railway expense and returns to the updated ledger row | P0 | Fixed | Tested pass | Keyboard could leave Update ledger partially off-screen in the UI test path; save/delete now dismiss keyboard and test helper resolves toolbar Done reliably. | Fixed | Passed
IOS-INK-014 | iOS Ink Entries | Delete Entry | As an ink ledger user, I can delete an existing entry and return to the empty ledger state. | Edit mode exposes Delete entry; deleting clears the row, reloads state, and returns to ledger.empty when no entries remain. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanCreateEditDeleteAndFinalizeInkLedger deletes a live Railway expense and returns to ledger.empty | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-015 | iOS Ink Entries | Split Participants | As an ink ledger user, I can include/exclude participants while keeping at least one person in the split. | Split person rows toggle selected state; the last selected participant cannot be removed; per-person equal amount updates from selected count. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanAddFriendSplitExpenseAndRecordSettlement verifies the seeded Railway friend is selected in the equal split; prototype test covers selected/not-selected toggling | P1 | Fixed | Tested pass | SwiftUI Button row did not toggle reliably while keyboard/ScrollView were active; row now uses custom tap/accessibility action and dismisses keyboard. | Fixed | Passed
IOS-INK-016 | iOS Ink Settle | Settle Screen | As an ink ledger user, I can view simplified settlements for a trip. | Settle screen reads store.settlements(for:), filters user-relevant settlement actions, supports trip selection, refresh, settings, and record payment sheet. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanAddFriendSplitExpenseAndRecordSettlement creates a live two-person debt and opens settlementRow.0 | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-017 | iOS Ink Payments | Record Payment | As an ink ledger user, I can record a settlement payment involving me. | RecordPayment modal selects trip/counterparty/direction/method/amount and posts /api/mobile/transactions via InkTripStore.recordSettlement. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testRailwayCanAddFriendSplitExpenseAndRecordSettlement records the live Railway settlement and clears the payment path | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-018 | iOS Ink Finalization | Finalize Ledger and Final Bill | As a ledger user/admin, I can mark a ledger final and review the final bill. | Live ledger exposes finalization for open ledgers; store posts /api/mobile/groups/{id}/finalize; FinalBill shows total/summary and routes back to ledger history. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift; apps/web/app/api/mobile/groups/[id]/finalize/route.ts | testRailwayCanCreateEditDeleteAndFinalizeInkLedger; testRailwayCanAddFriendSplitExpenseAndRecordSettlement; prototype final-bill launch tests | P0 | Fixed | Tested pass | Direct final-bill launch initially lacked selected trip state; launch-state preselection now covers final bill and ledger routes. | Fixed | Passed
IOS-INK-019 | iOS Ink Navigation | Bottom Tabs | As an ink app user, I can switch between trips/settle/profile where those tabs are visible. | InkBottomTabs renders visible tab sets per screen and routes through handleTab. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift | testPrototypeSettleRecordPaymentAndBottomTabs | P1 | Fixed | Tested pass | Trips screen hid Ledger/Settle tabs and a parent identifier overwrote child tab identifiers; tabs now retain full hit targets and stable identifiers. | Fixed | Passed
IOS-INK-020 | iOS Ink Profile | Profile and Logout | As a signed-in ink app user, I can view account/profile information and sign out. | Profile tab reads the current user/account state and routes logout through AuthStore. | apps/ios/BillBanditApp/Sources/BillBanditInkPrototypeView.swift; apps/ios/BillBanditApp/Sources/BillBanditApp.swift | testRailwayOTPAuthSignsIntoReceiptTrips taps Profile and signs out against Railway-backed auth | P1 | Fixed | Tested pass | Profile tab previously opened the New Member account-creation screen for signed-in users; it now shows account profile and Sign out. | Fixed | Passed
IOS-INK-021 | iOS Ink QA | Mock API and Launch Modes | As maintainers, we can run deterministic local and Railway-backed iOS flows. | MockBillBanditAPI, --root=prototype, --ink-screen, --volatile-auth-session, --reset-auth-session, and API_BASE_URL build setting support deterministic tests. | apps/ios/BillBanditApp/Sources/MockBillBanditAPI.swift; apps/ios/BillBanditApp/UITests/BillBanditUITests.swift | Normal iOS suite passes with Railway UI tests skipped by opt-in guard; opt-in Railway UI suite passes 3/3 against production URL | P0 | Implemented | Tested pass |  | N/A | Passed
IOS-INK-022 | iOS Native Tabs | Dashboard/Groups/Group Detail/Expense Editor | As a user outside the ink shell, I can use the native tab-based dashboard, groups, group detail, add member, expense editor, and settle-up views. | MainTabView hosts DashboardView, GroupsView, GroupDetailView, ExpenseEditorView, AddMemberView, and SettleUpView against mobile API models. | apps/ios/BillBanditApp/Sources/DashboardView.swift; GroupsView.swift; GroupDetailView.swift; ExpenseEditorView.swift; SettleUpView.swift | No focused UI coverage in this pass; user asked to focus on the blue/cream ink build | P2 | Deferred | Deferred by scope | Out of current scope unless user reopens native tab UI testing. | N/A | N/A

## Errors & Fixes
Error ID | Surface | Finding | Resolution / Evidence | Linked Story | Discovery | Fix Status | Severity | Retest
IOS-ERR-001 | iOS Ink Members | Remote add friend/member used username while Railway mobile member route requires email. | Updated AddFriend copy, validation, lookup, store request, MockBillBanditAPI, and unit input to use BillBandit email. | IOS-INK-010 | Code audit + mobile API contract | Fixed | High | Passed
IOS-ERR-002 | iOS Ink Entries | Editing an expense could leave Update ledger competing with the keyboard/off-screen hit target in UI testing. | AddEntry save/delete now dismiss keyboard; UI helper taps keyboard.done reliably; focused edit test passed. | IOS-INK-013 | XCTest failure in testPrototypeLedgerCanAddEditAndDeleteExpense | Fixed | High | Passed
IOS-ERR-003 | iOS Ink Auth/Entries | XCTest could see multiple keyboard.done accessibility matches and fail to tap the keyboard toolbar. | dismissKeyboardIfNeeded now queries firstMatch by identifier/label and waits for the keyboard to disappear. | IOS-INK-005; IOS-INK-013 | XCTest failure in testMockAppleAuthCompletesProfileAndReachesTrips | Fixed | Medium | Passed
IOS-ERR-004 | iOS Ink Auth | Railway OTP smoke assumed the post-auth trips screen would always be empty. | Live test now accepts empty trips, your-expenses copy, no-expenses copy, or tripCard.* rows from real Railway data. | IOS-INK-004; IOS-INK-007 | XCTest failure in testRailwayOTPAuthSignsIntoReceiptTrips | Fixed | Medium | Passed
IOS-ERR-005 | iOS Ink Navigation | Trips tab did not navigate reliably from Settle, and the parent trips-screen accessibility identifier overwrote child bottom-tab identifiers. | Expanded bottom-tab hit targets, removed the parent container identifier, restored full tabs on populated Trips, and asserted real trip cards after tab navigation. | IOS-INK-019 | XCTest failure in testPrototypeSettleRecordPaymentAndBottomTabs | Fixed | Medium | Passed
IOS-ERR-006 | iOS Ink Entries | Split participant rows did not toggle reliably while a text field kept the keyboard active inside a ScrollView. | Replaced the split row Button with a custom tap/accessibility action row, added stable selected/not-selected accessibility values, and dismisses the keyboard before toggling. | IOS-INK-015 | Repeated XCTest failure in testPrototypeLedgerCanAddEditAndDeleteExpense | Fixed | Medium | Passed
IOS-ERR-007 | iOS Ink Profile | Profile tab opened the New Member account-creation screen for signed-in users. | Added ProfileInkScreen with account details and Sign out, wired logout through BillBanditApp, and covered it in the live Railway OTP UI test. | IOS-INK-020 | Code audit + user story coverage | Fixed | High | Passed
IOS-ERR-008 | iOS Ink Final Bill | Direct final-bill launch did not preselect a trip, making See all unable to return to the ledger. | Launch-state preselection now includes live ledger, settle, record payment, final bill, and add entry screens. | IOS-INK-018 | XCTest failure in testPrototypeFinalBillSeeAllReturnsToLedger | Fixed | Medium | Passed
IOS-ERR-009 | iOS UI Test Harness | The first live Railway expense-edit test appended the edited title instead of replacing the existing title. | Updated replaceText usage so existing expense titles are treated as real content, not placeholders; reran the live Railway ledger CRUD/finalize flow successfully. | IOS-INK-013 | XCTest failure in testRailwayCanCreateEditDeleteAndFinalizeInkLedger | Fixed | Medium | Passed
IOS-ERR-010 | iOS Add Friend Flow | The live add-friend test assumed only the Add friend button submits, but keyboard Done can submit after Account found and return to the ledger. | Adjusted the UI test to accept either keyboard submission or explicit save-button submission, then reran the live Railway add-friend/split/settlement/finalize flow successfully. | IOS-INK-010 | XCTest failure in testRailwayCanAddFriendSplitExpenseAndRecordSettlement | Fixed | Low | Passed
WEB-DEF-001 | Web UI | Dashboard add-expense Playwright failure is deferred by user request. | Web run had 52 passed, 1 skipped, 1 dashboard add-expense failure; user said to skip web and focus iOS. | Deferred Web | Production Playwright run before scope change | Deferred | Medium | N/A

## Test Evidence
Date | Layer | Command / Probe | Result | Notes
2026-06-22 | iOS isolated simulator | Created and booted simulator BillBandit Ink QA - Codex (1CF86119-E6D0-406E-BD00-E18F2C57CACF) | Passed | All subsequent iOS test evidence in this workbook uses only this simulator to avoid clashing with other test threads.
2026-06-22 | iOS regression | xcodebuild test -destination id=1CF86119-E6D0-406E-BD00-E18F2C57CACF COMPILER_INDEX_STORE_ENABLE=NO | Passed | 13 passed, 0 failed, 3 skipped. The skipped tests are the opt-in Railway UI mutation tests.
2026-06-22 | Railway iOS live UI suite | xcodebuild test -destination id=1CF86119-E6D0-406E-BD00-E18F2C57CACF -only-testing:testRailwayOTPAuthSignsIntoReceiptTrips -only-testing:testRailwayCanCreateEditDeleteAndFinalizeInkLedger -only-testing:testRailwayCanAddFriendSplitExpenseAndRecordSettlement API_BASE_URL=https://billbandit-api.contenthelper.in | Passed | 3 passed, 0 failed against Railway production URL with BILLBANDIT_RUN_RAILWAY_UI_TESTS=1.
2026-06-22 | Railway iOS ledger CRUD | testRailwayCanCreateEditDeleteAndFinalizeInkLedger | Passed | Live UI created a Railway ledger, added an expense, edited it, deleted it, saw ledger.empty, marked final, and returned from Final Bill.
2026-06-22 | Railway iOS friends/payments | testRailwayCanAddFriendSplitExpenseAndRecordSettlement | Passed | Live UI seeded a registered friend, added that friend by email, created a two-person split, opened settlementRow.0, recorded payment, and finalized.
2026-06-22 | Railway QA data cleanup | Mobile API finalized active Codex QA ledgers left by failed live-test attempts | Passed | Finalized Codex QA Settle 1782142034 and Codex QA 1782141468 so QA ledgers are not left active in Railway.
2026-06-22 | iOS focused UI | testPrototypeLedgerCanAddEditAndDeleteExpense | Passed | Focused ledger test covers create ledger, add entry, split toggle, edit entry, delete entry, and empty-state return.
2026-06-22 | iOS focused UI | testPrototypeSettleRecordPaymentAndBottomTabs; testPrototypeCanMarkLedgerFinalAndReturnToLedger | Passed | Focused tests cover bottom-tab switching, settlement row, record-payment modal, mark-final flow, final-bill See all return.

## Deferred Web
Surface | Feature | Status | Reason
Web UI | Dashboard add expense | Deferred | The production Playwright run found a dashboard add-expense race/context issue. User explicitly asked to skip the web interface for now.
Web UI/API | Other previously tracked web findings | Deferred | Remain documented from prior audit but are not part of the current blue/cream iOS ink pass.